PROGRESS REPORT

Mustang Island Habitat Protection and Enhancement

14-095-000-7963

FINAL REPORT 2015

Task 1:  Project Designs and Contractor Selection

- Task Status:  not started in progress completed

- Describe major accomplishments for this reporting period (include names of staff working on each task, dates and locations of events/presentations/meetings and dates for milestones/deliverables completed).

CBBEP contracted with G&W Engineers to develop the final design and specifications to repair and install new and existing bollards and cables around Packery Flats Coastal Habitat and Kate’s Hole preserves and remove debris from the sites. CBBEP developed bid/contract documents for the bid solicitation. All contracting and bidding was conducted in accordance with the state procurement policy. The contract for services was dated July 1, 2014. CBBEP received a letter of permission from the U.S. Army Corps of Engineers to install bollards within the waters of the U.S. on September 2, 2014. CBBEP submitted the bid/contract documents and designs to the GLO for approval prior to soliciting bids. On December 10, 2014, CBBEP received permission from the GLO and NOAA to move forward with advertising the project for bid. CBBEP advertised the project for bid and selected Copano Bay Excavation as the construction contractor. CBBEP awarded the construction contract in the amount of $99,377 to Copano Bay Excavation.  The contractor began rebuilding the access road and parking lot on February 25, 2015.

- List the deliverable(s)/milestone(s) for the task and provide the date completed/submitted to the GLO.

| Deliverable Name | Date Due | Date submitted | Comments |
| --- | --- | --- | --- |
| Project Design, Specifications, and Bid/Contract Documents, due to GLO for review/approval prior to soliciting bids | October 31, 2014 | October 9, 2014 |  |
| Copies of executed contracts and notices to proceed, due upon receipt. | October 31, 2014 | March 10, 2015 |  |

- Were there any problems or obstacles encountered during this reporting period (e.g., delays, remedial action taken, schedule revision).  Yes 	No  	If yes, please explain:

Task 2:  Construction and Debris Removal

- Task Status:  not started in progress completed

- Describe major accomplishments for this reporting period (include names of staff working on each task, dates and locations of events/presentations/meetings and dates for milestones/deliverables completed.)

The contractor removed the concrete debris from the wetlands to provide a better functioning coastal marsh and tidal habitat and added the specified tonnage of limestone road base to the access roads and parking areas to provide safe public access.  The construction contractor installed new cables and bollards and repaired existing cables and bollards according to the project design and specifications developed by the engineer. Construction activities were completed on June 25, 2015.

- List the deliverable(s)/milestone(s) for the task and provide the date completed/submitted to the GLO.

| Deliverable Name | Date Due | Date submitted | Comments |
| --- | --- | --- | --- |
| Provide photos before, during, and after construction and removal activities | July 15, 2015 | July 9, 2015 |  |

- Were there any problems or obstacles encountered during this reporting period (e.g., delays, remedial action taken, schedule revision).  Yes 	No  	If yes, please explain:

The bollards installed for the project have a higher treatment level than those readily kept in stock at local stores.  CBBEP ordered 700 bollards from a company that supplied bollards to the project specifications.  The bollards took four weeks to deliver.  The time delay on the materials and the weather delays required an extension. Additionally, higher than average spring tides caused the contractor to use a jet pump to install the last of the bollards.  CBBEP received a budget amendment and also a contract extension for time to complete the project.

Task 3:  Interpretive Signage

- Task Status:  not started in progress completed

- Describe major accomplishments for this reporting period (include names of staff working on each task, dates and locations of events/presentations/meetings and dates for milestones/deliverables completed.)
CBBEP coordinated with local project partners, including GLO field staff, to develop educational signage for the project site.  CBBEP hired Snyder & Associates to assist with the sign layout and design.  CBBEP submitted the conceptual sign design to the GLO for review and approval prior to fabricating and installing.  The GLO reviewed the draft signage and provided comments. The sign designer revised the final layout, which was approved by CBBEP on July 7, 2015. The signs include CMP and NOAA logos and funding statement. CBBEP ordered the signs from IZone, which provides a 10-year guarantee against fading, peeling, or cracking. Interpretive signage was installed at the project site.

Brad Snyder-Snyder and Associates (sign design)

Jake Herring- CBBEP (sign review and coordination)

Jesse Solis- GLO (sign review, provide information)

Jennifer Lawrence- GLO (sign review, provide information)

- List the deliverable(s)/milestone(s) for the task and provide the date completed/submitted to the GLO.

| Deliverable Name | Date Due | Date submitted | Comments |
| --- | --- | --- | --- |
| Sign layout for GLO review/approval | June 30, 2015 | April 30, 2015 |  |
| Photos of installed signage | July 31, 2015 | August 10, 2015 |  |

- Were there any problems or obstacles encountered during this reporting period (e.g., delays, remedial action taken, schedule revision).  Yes 	No  	If yes, please explain:

Signage design took longer than anticipated.  CBBEP continued to work with the design team at Snyder & Associates to make sure the sign designs projected the intended message intended for the project.  It was desired that the signs be informative and educational without being too technical for the everyday user of the public access area.  In future projects CBBEP will allow more time for signage design.

Task 4:  Project Monitoring and Reporting

- Task Status:  not started in progress completed

- Describe major accomplishments for this reporting period (include names of staff working on each task, dates and locations of events/presentations/meetings and dates for milestones/deliverables completed.)

The project is complete.

- List the deliverable(s)/milestone(s) for the task and provide the date completed/submitted to the GLO.

| Deliverable Name | Date Due | Date submitted | Comments |
| --- | --- | --- | --- |
| Grant Closeout Report | July 31, 2015 | August 10, 2015 |  |

| Reimbursement requests no. | Date Submitted | Comments |
| --- | --- | --- |
| Continue as needed to document invoices submitted |  |  |

- Were there any problems or obstacles encountered during this reporting period (e.g., delays, remedial action taken, schedule revision).  Yes 	No  	If yes, please explain:

Please provide a current budget breakdown.  (Double Click on budget tables to activate Excel.)

*Obligated includes - funds that have been incurred by the recipient but have not been paid by the recipient, such as executed contract agreements or acquired supplies/materials/equipment.